## Introduction
Revised February 16, 2010
ACH
Merchant Cards
Yahoo Stores
PayPoint
Project Plan for Implementing Electronic Payment Program
For Either
Electronic Funds Transfer (ACH)
Or
Merchant Cards
(POS Terminals / 3rd Party Gateway / Yahoo Store / PayPoint)
Instructions
This project plan identifies the tasks necessary to implement an Electronic Payment Program, for either "Merchant Cards" or "Electronic Funds Transfer (ACH)," and for which the Common Payment Service (CPS) gateway is NOT involved. (A separate plan for projects involving CPS can be found on the CPS section of the SECP Website.) The plan identifies the corresponding tasks for which both the participanting agency and the Office of the State Controller (OSC) are responsible.
There are several versions of the plan, depending upon the project being implemented, with each version having a different tab below. There is one tab for "ACH Implementation;" one tab for "Merchant Cards;" one tab for "Merchant Cards - Yahoo Store;" and one tab for "Paypoint." Each plan is formatted such that your organization's tasks and deliverables are identified in columns C, D and E. Those tasks and deliverables for which OSC is responsible are identified in columns F, G and H.
Prior to completion, information on OSC's Website should be reviewed. http://www.osc.nc.gov/SECP/EPP_Index.html
The plan is also outlined in Power Point Presentations found on OSC's SECP Website.

## ACH - Implementation
| ACH Implementation Plan | Name of Agency: |  |  | Revised | 2010-02-18
| Website link for Presentation: | http://www.osc.nc.gov/SECP/SECP_EFT_Enrollment.html | OSC Support Services Center Contact Info: |  | 919.707.0795
NOTE: This plan does not apply if participants are utilizing the Common Payment Services (CPS) Gateway (See CPS Implementation Plan)
| AGENCY ACTIVITIES & TASKS |  |  | OSC ACTIVITIES & TASKS
Step | AGENCY ACTIVITIES & TASKS | TASK DESCRIPTION | Agency/Project Deliverables | CORRESPONDING TASKS (OSC Use Only) | By | Date Completed
1 | Idenfify EFT Project |  |  | OSC provides updated Website information and answers any questions asked. | OSC
1.1 | Review information on OSC's SECP Website | Review presentations, policies, agreements, and forms. The Internal Policies and Procedures Template is a most useful document to identify tasks to be performed.
1.2 | Idenfity potential payment applications | Identify Outbound or Inbound payments, authority, and if mandatory or voluntary participation
1.3 | Determine systems for database maintenance | Identify system for payee/payor database for associated bank account information
1.4 | Determine method of ACH file transmission | Identify method of creating and submitting ACH files (FTP, VAN, WebAchieve, etc).
1.5 | Develop internal statement of work | Identify work to be performed, resources needed, security measures, timeframes, etc. | Statement of Work
1.5a | Obtain assistance from OSC | Request Pre-Project meetings for discussions. Topics include security requirements; source of application servers; involvement of IT staff. |  | OSC meets with Agency, and with Wachovia if necessary | OSC
1.6 | Assess feasibility of implementation | Cost-benfit analysis Includes costs of development and ongoing operation maintaince. | Cost-benefit analysis
1.7 | Obtain management approval for project | Consider cost-benefit analysis, staffing, and funding | Project Plan
1.8 | Obtain ITS Project Management Office approval | Enroll with ITS Project Portfolio Management (PPM), if applicable
Other
2 | Execute Enrollment Forms |  |  | OSC provides all forms on Website | OSC
2.1 | Master Services Agreement (MSA) | Review MSA. Legal should review agreement
2.2 | Agency Participation Agreement (APA) | Execute APA. Legal should review agrrement | APA | OSC approves or disapproves participation | OSC
2.3 | EFT Participant Setup Form | Execute Participate Setup Form - by Chief Fiscal Officer | EFT Participant Setup Form | OSC processes form with DST & Wachovia | OSC
|  |  |  | OSC adds the contact to the SECP Email Contact List | OSC
2.4 | ACH Manager Setup Form | If ACH Manager is method of transmission, execute ACH Manager Setup Form | ACH Manager Setup Form | OSC processes form with Wachovia | OSC
3 | OSC Acts on Enrollment Forms
3.1 | Agency Participation Agreement (APA) |  |  | OSC processes agreements with DST and Wachovia, & distributes | OSC
3.2 | EFT Participant Setup Form |  |  | OSC processes form with DST and Wachovia | OSC
|  |  |  | If OSC is Admin for Wachovia Connection, agency users are set up, and users are notified of their UserID and initial password. | OSC
4 | DST Acts on Enrollment Forms
4.1 | Agency Participation Agreement (APA) |  |  | DST executes APA, if State agency | DST
4.2 | EFT Participant Setup Form |  |  | DST authorizes Wachovia to establish Settlement account and Returns account (for inbound) | DST
|  |  |  | DST determines if it will pay fees for bank account, or if participant will | DST
|  |  |  | If inbound transactions, establishes CIT account on CB$ and maps the ZBA account number when received from Wachovia, if State agency | DST
4.3 | CB$ Electronic Warrant Template Form |  | CB$ Request For Electronic Warrant Form | If outbound transactions, establishes Electronic Warrant template on CB$, and sets up corresponding repetitive wire instructions on Wachovia Connection, if State agency. | DST
5 | Wachovia Acts on Enrollment Forms
5.1 | Agency Participation Agreement (APA) |  |  | Wachovia executes APA and returns to OSC | Wach
5.2 | EFT Participant Setup Form |  |  | Wachovia sets up transmission link with either CPS or participant | Wach
|  |  |  | Wachovia sets up settlement bank account, and Returns account if inbound, and advises DST and OSC of account numbers | Wach
|  |  |  | Wachovia links account to Wachovia Connection Administrator | Wach
|  |  |  | Wachovia sets up invoicing | Wach
|  |  |  | Wachovia sets up statement rendering | Wach
5.3 | ACH Manager Setup Form | Applies only if ACH Manager is method of transmission |  | Wachovia sets up Agency Admin, and users as specified on setup form | Wach
|  |  |  | Wachovia provides Confirmation Package to agency | Wach
6 | Establish file transmission and Testing
6.1 | Use Standard NACHA Format for file creation | View file layout on OSC's SECP Website, and if agency creates file, perform program development
6.2 | Setup transmission mechanism | Define transmission requirements, establish testing environment, and develop any required interfaces or network connections, or FTP, or VAN services
6.3 | Develop Test Plan and Application specific Test Script | Obtain assistance from Wachovia for performing testing
6.4 | Perform testing of file transmission | Obtain assistance from Wachovia for performing testing
6.5 | Perform Prenotification Transaction (mandatory for payroll, but optional for vendors) | Agency may determine to send a Prenote (Zero Dollar) transaction through the ACH network. If a Prenote transactions if sent, there must be a six banking day lag before a live transaction can be initiated.
6.6 | Perform "production verification" | Production Verification means the agency application is live and will accept and process LIMITED live transactions from pre-identified employees or vendors. The purpose is to determine if the agency's application has been set-up correctly: funds are either remitted are received by the payees/payors on the date anticipated, and the settlement bank account (and Returns account if applicable) can be viewed through Wachovia Connection. Any incorrect set-ups have to be corrected before being put into full production.
6.7 | Resolve agency set-up issues detected | Report findings to OSC. OSC will work with Wachovia Bank for any account set-up issues. |  | Make any necessary changes in account mapping on Wachovia Connection. | OSC
|  |  |  | Make any necessary changes in users on ACH Manager. | Wach
7 | Establish Fiscal Procedures |  | Link to Template
7.1 | Educate staff on SECP website | Review presentations, policies, agreements, forms, and contact information
7.2 | Establish procedures for funding outbound ACH transactions, and Returns | Incorporate Reconcilement Function requirements on SECP website
7.3 | Establish procedures for reporting of inbound ACH transactions, and Returns | Incorporate Reconcilement Function requirements on SECP website
7.4 | Establish procedures for Wachovia Connection users | Verify all users have received userIDs and passwords, and have access to all required functions and settlement accounts
7.5 | Establlish procedures for reviewing, verifying, and paying Wachovia monthly invoice, unless DST pays fees. | Develop controls, and examine to enusre that the appropriate fees are being applied.
7.6 | Establish procedures for obtaining ACH authorizations from payees/payors | Develop forms for initial enrollment and subsequent changes (bank account information), and updating database for any subsequent changes, including prenotes.
7.7 | Prepare an updated Cash Management Plan | Describe Internal Policies and Procedures, incorporating procedures established, and any applicable E-Commerce policies on SECP websie, utilizing sample format. | Internal Policies and Procedures
7.8 | Submit Internal Agency Policies & Procedures | Submit by email to osc.secp.info@ncosc.net for review. |  | OSC reviews and approves policies and procedures | OSC

## Merchant Cards
| Merchant Card POS Terminal Implementation Plan | Name of Agency: |  |  | Revised | 2010-02-18
| Website link for Presentation: | http://www.osc.nc.gov/SECP/SECP_MerchantCard_Enrollment.html |  | OSC Support Services Center Contact Info: | 919.707.0795
NOTE: This plan does not apply if participants are utilizing the Common Payment Services (CPS) Gateway (See CPS Implementation Plan)
| AGENCY ACTIVITIES & TASKS |  |  | OSC ACTIVITIES & TASKS
Step | AGENCY ACTIVITIES & TASKS | TASK DESCRIPTION | Agency/Project Deliverables | CORRESPONDING TASKS (OSC Use Only) | By | Date Completed
1 | Idenfify Merchant Card Project |  |  | OSC provides updated Website information and answers any questions asked. | OSC
1.1 | Review information on OSC's SECP Website | Review presentations, policies, agreements, and forms, including PCI Security Standards information. The Internal Policies and Procedures Template is a most useful document to identify tasks to be performed.
1.2 | Idenfity potential payment applications | Identify "card-present" and "card not-present" situations. Determine which cards will be accepted (Visa, MasterCard, AmEx, etc)
1.3 | Determine capture methods to be used | Consider POS stand-alone Terminals, POS Terminals with Electronic software, Web-based applications, Third-party Gateway (If third-party gateway used, must obtain approval from OSC). If POS terminals, determine if purchase, rent, or lease. |  | OSC considers any business case for use of third-party gateway instead of CPS, if a gateway service is used. Approval of 3rd party POS software by OSC is not required. | OSC
1.4 | Determine method of transmission | Identify method of transmitting authorizations and batch transactions (Analog telephone line for stand-alone POS terminals).
1.5 | Develop internal statement of work | Identify work to be performed, resources needed, security measures, timeframes, etc. | Statement of Work
1.5a | Obtain assistance from OSC and/or CPS | Request Pre-Project meetings or conference call for discussions. Topics include security requirements; source of application servers; involvement of IT staff. Determine ability to compy with PCI Security Standards. |  | OSC participantes in meeting or conference call | OSC
1.6 | Assess feasibility of implementation | Cost-benfit analysis Includes costs of development and ongoing operation maintaince. | Cost-benefit analysis
1.7 | Obtain management approval for project | Consider cost-benefit analysis, staffing, and funding | Project Plan
1.8 | Obtain ITS Project Management Office approval | Enroll with ITS Project Portfolio Management (PPM), if applicable
1.9 | Determine if convenience fee will be levied. | Consider OSC policy and obtain approval from OSBM. Consider Rules of card associations for cards being accepted.
1.10 | Determine how PCI Security Compliance applies | Consider PCI requirements on OSC's document "Applicability of PCI Data Security to Capture Methods"
Other
2 | Execute Enrollment Forms |  | Link To Forms | OSC provides all forms on Website | OSC
2.1 | Master Services Agreement (MSA) | Review MSA. Legal should review agreement. Consider the potential fines and other liabilites.
2.2 | Agency Participation Agreement (APA) | Execute APA. Legal should review agrrement. | APA | OSC approves or disapproves participation. A new APA is not required for subsequently added outlets. | OSC
2.3 | Merchant Card Participant Setup Form | Execute Participate Setup Form - by Chief Fiscal Officer |  | A new Participant Setup Form is not required for subsequently added outlets.
2.4 | Merchant Card Outlet Setup Form | Execute Outlet Setup Form for each outlet or line of business (merchant number) needed - by Fiscal Officer | Merchant Card Outlet Setup Form
2.5 | ClientLine Setup Form | Prepare form designating users who will need access to ClientLine online reporting with STMS - by Fiscal Officer | ClientLine Setup Form
2.6 | POS Terminal Order Form | View info on OSC's SECP site regarding various terminals available, determine quantity needed, and determine if will be purchased, rented, or leased | POS Terminal Order Form
2.7 | Wachovia Connection Setup Form | Prepare form designating users who will need access to Wachovia Connection online reporting for the Wachovia bank settlement account - by Fiscal Officer | Wachovia Connection Setup Form
2.8 | PCI Security Validation Services Pre-Enrollment Form | Execute PCI Pre-Enrollment Form, if not currently enrolled in TrustKeeper - by Agency's PCI Contact. Agency must pick between two options: 1) SAQ only; or 2) SAQ and Vulnerability Scanning. | PCI Data Security Validation Services Pre-Enrollment Form
3 | OSC Acts on Enrollment Forms
3.1 | Agency Participation Agreement (APA) |  |  | OSC processes agreements with DST and STMS, & distributes | OSC
3.2 | EFT Participant Setup Form |  |  | OSC processes form with DST, STMS, & Wachovia | OSC
|  |  |  | OSC updates the participant info in the Access database, and email contact list | OSC
3.3 | Merchant Card Outlet Setup Form |  |  | OSC processes form with STMS, and updates the Access database with the Merchant info | OSC
3.4 | ClientLine Setup Form |  |  | OSC processes from with STMS, setting up users and obtaining UserIDs and initial passwords. Users are notified directly of their UserIDs and initial passwords. | OSC
3.5 | POS Terminal Order Form |  |  | If POS terminals are needed, OSC orders the terminals from STMS, with delivery being made directly to agency | OSC
3.6 | Wachovia Connection Setup Form |  |  | If OSC is Admin for Wachovia Connection, agency users are set up, and users are notified directly of their UserID and initial password. | OSC
3.7 | PCI Security Validation Services Pre-Enrollment Form |  |  | The agency completes the enrollment of the agency's chain number in TrustKeeper. If application involves external-facing IP addresses, each address must be enrolled in TrustKeeper for monthly vulnerability scanning. | OSC
4 | DST Acts on Enrollment Forms
4.1 | Agency Participation Agreement (APA) |  |  | DST executes APA | DST
4.2 | Merchant Card Participant Setup Form |  |  | DST authorizes Wachovia to establish settlement account for agency | DST
|  |  |  | DST establishes CIT account on CB$, and maps the ZBA account number when received from Wachovia, if State agency | DST
5 | STMS Acts on Enrollment Forms
5.1 | Agency Participation Agreement (APA) |  |  | STMS executes APA and returns to OSC. Non-State agencies may be subject to a credit check | STMS
5.2 | Merchant Card Participant Setup Form |  |  | STMS sets up profile for agency, assigning a Chain Number tor the agency Merchant Name, and advises OSC | STMS
5.3 | Merchant Card Outlet Setup Form |  |  | STMS assigns a merchant number to each outlet, mapping them to the agency's chain number. Also sets up invoicing. | STMS
5.4 | ClientLine Setup Form |  |  | STMS sets up users and provides UserIDs and initial passwords to OSC, which then notifies each user separately, normally by Fax. | STMS
5.5 | POS Teminal Order Form |  |  | If terminals are ordered, STMS ships terminals directly to agency. Setup package will be included. | STMS
6 | Establish production environment and Testing
6.1 | Issue requisition/purchase order for equipment and / or software | Follow agency's internal procurement procedures
6.2 | Order and install dedicated phone line for equipment | Contact local telephone vendor.
6.3 | Receive equipment and schedule phone-based training | Within two weeks from receipt of order STMS will deliver equipment loaded with software, along with a package of information regarding setup instructions and testing. Request phone-based training from STMS - per instructions in package.
6.4 | Perform testing of limited transactions | Perform testing per instructions in package. Additionally, OSC has a set of "test merchant card numbers" that can be used to test (Visa, MC, AmEx, and Discover). These test card numbers will appear on MyMerchant View, but do not result in money transactions to the bank settlement account.
6.5 | Resolve agency set-up issues detected | STMS will assist in transaction issues. OSC will work with Wachovia Bank for any account set-up issues. |  | Make any necessary changes in account mapping on Wachovia Connection. | OSC
|  |  |  | Make any necessary changes in users on MyMerchant View. | OSC
7 | Establish Business Procedures |  | Link to Template
7.1 | Educate staff on SECP website | Review presentations, policies, agreements, forms, and contact information
7.2 | Establish procedures for face-to-face transactions and card not-present transactions. | Base procedures on STMS Operating Guide and Card Association Rules. Topics should include signature verification, address verification, expiration date verification, processing inadvertent duplicate transactions, refunds, chargebacks, etc.
7.3 | Establish procedures for obtaining authorizations | Base procedures on STMS Operating Guide and Card Association Rules. Topics should include voice authorization as backup, suspected fraud situations (Code 10 Procedures), etc.
7.4 | Provide necessary training for operating POS terminals and POS software applications. | Obtain guidance from STMS Technical Services Help Desk if necessary.
7.5 | Establish procedures for closing out terminals and other applications, and tranmitting batches to either CPS or STMS. | Base procedures based on cut-off times provided by CPS or STMS.
7.6 | Establish procedures for retaining transaction slips, records retention, and handling disputed transactions. | Devise procedures based on OSC E-Commerc Policies, STMS Operating Guide, and Card Association Rules. Use template on OSC's SECP Website | Internal Policies and Procedures
7.7 | Submit Internal Agency Policies & Procedures | Submit by email to osc.secp.info@ncosc.net for review. |  | OSC reviews and approves policies and procedures | OSC
8 | Establish Fiscal Procedures |  | Link to Template
8.1 | Educate staff on SECP website | Review presentations, policies, agreements, forms, and contact information
8.2 | Establish procedures for reporting of funds received for settlement of transactions; and Refunds and Chargebacks that are netted out of daily ZBA sweep. | Incorporate Reconcilement Function requirements on SECP website. Consider settlement of proprietary card transactions that may be received on a different day than Visa or MasterCard.
8.3 | Establish procedures for Wachovia Connection users | Verify all users have received userIDs and passwords, and have access to all required functions and settlement accounts
8.4 | Establish procedures for ClientLine users | Verify all users have received userIDs and passwords, and have access to all merchant numbers and required reports
8.5 | Establish procedures for VCCT users | Verify all users have received userIDs and passwords, and have access to all merchant numbers and required reports
8.6 | Establish procedures for multiple merchant number settling into same bank account, and associated reconcilement with the decentralized department's captured transactions. | Incorporate Reconcilement Function requirements on SECP website
8.7 | Establlish procedures for reviewing, verifying, and paying STMS monthly invoice | Develop controls, and periodically examine to enusre that the appropriate Interchange rates are being applied.
8.8 | Prepare an updated Cash Management Plan | Describe Internal Policies and Procedures, incorporating procedures established, and any applicable E-Commerce policies on SECP websie, utilizing sample format. | Internal Policies and Procedures
8.9 | Submit Internal Agency Policies & Procedures | Submit by email to osc.secp.info@osc.nc.gov for review. |  | OSC reviews and approves policies and procedures | OSC
9 | Validate PCI Compliance |  | Link to PCI Info
9.1 | Educate staff on PCI Security Standards requirements | Review OSC's Website pertaiing to PCI Security, including presentations, policies, Visa and MasterCard Websites. Consider the potential fines for non-compliance or security breaches.
9.2 | Establish procedures from the business perspective | Consider requirement associated with business processing, to include physical security, and employee screening, etc.
9.3 | Establish procedures from the technical perspective | Consider requirement associated with technical processing, to include hardware, software, firewalls, encryption, etc.
9.4 | Complete Security Assessment Questionnaire | Select the appropriate SAQ, likely either SAQ-A, B, C, or D. To be completed online annually.
9.5 | Ascertain compliance of third party providers | If third-party gateways or other service providers are used, obtain certificate of compliance, pursuant to Requirement 12.8. Need written agreement regarding compliance.
9.6 | Designate individual for PCI Security | Provide one contact for entire agency to OSC, on Merchant Card Participant Setup Form
9.7 | Enroll in TrustKeepr Portal with Trustwave | If the application involves external-facing IP address, the addresses must be enrolled for vulnerability scanning. The enrollment should be for both "SAQ and Vulnerability Scanning," with the scanning be perfomed by Trustwave monthly. |  | OSC pre-enrolls the agency in TrustKeeper based on Pre-enrollment form. Agency must complete the enrollment via TrustKeeper. Agency must specify the external-facing IP addresses to be scanned monthly. | OSC
9.8 | Establish Procedures for PCI Remediation | Estabhilsh procedures for compliance deficiencies detected in annual SAQ or in monthly vulnerability scan

## Merchant Cards - YahooStore
| Merchant Card Yahoo Store Implementation Plan | Name of Agency: |  |  | Revised | 2010-02-18
| Website link for Presentation: | http://www.osc.nc.gov/SECP/SECP_MerchantCard_Enrollment.html |  | OSC Support Services Center Contact Info: | 919.707.0795
| Yahoo Merchants Solutions Site: | http://smallbusiness.yahoo.com/ecommerce/
NOTE: This plan does not apply if participants are utilizing the Common Payment Services (CPS) Gateway (See CPS Implementation Plan)
| AGENCY ACTIVITIES & TASKS |  |  | OSC and ITS ACTIVITIES & TASKS
Step | AGENCY ACTIVITIES & TASKS | TASK DESCRIPTION | Agency/Project Deliverables | CORRESPONDING TASKS (OSC & ITS Use Only) | By | Date Completed
1 | Idenfify Merchant Card Project |  |  | OSC provides updated Website information and answers any questions asked. | OSC
1.1 | Review information on OSC's SECP Website | Review presentations, policies, agreements, and forms, including PCI Security Standards information. The Internal Policies and Procedures Template is a most useful document to identify tasks to be performed.
1.2 | Idenfity potential payment applications | Determine what services or products will be available through Yahoo Store (products, registration, etc.) Determine which cards will be accepted (Visa, MasterCard, AmEx, etc) View other ageny stores on NCgov.com at: http://www.ncgov.com/store/catalog.asp Store will be listed as a NC@YourService Store
1.3 | Determine Yahoo Plan to subscribe to | Select the appropriate Yahoo Plan. Consider different features provided by "Yahoo! Merchant Solutions." View Yahoo Website: http://smallbusiness.yahoo.com/ecommerce/ Plans include: Starter, Standard, and Professional. Most agencies select the "Starter Plan," which provides a domain name and email accounts, suitable for transaction volume of less than $12,000 per month. Setup fee is $50; monthly maintenance fee is $39.95; transaction fee is 1.5% of transaction (this is in addition to the merchant card fees charged by STMS)
1.4 | Develop internal statement of work | Identify work to be performed to design and build the store, resources needed, security measures, timeframes, etc. Review Yahoo E-Commerce basics at: http://smallbusiness.yahoo.com/ecommerce/basics.php | Statement of Work
1.4a | Obtain assistance from OSC and/or ITS | Request Pre-Project meetings for discussions. Topics include security requirements; involvement of IT staff. Determine ability to compy with PCI Security Standards. |  | OSC discusses with Agency Agency is referred to ITS for assistance design and building of initial store | OSC ITS
1.4b | Assess feasibility of implementation | Cost-benfit analysis Includes costs of development and ongoing operation maintaince. | Cost-benefit analysis
1.5 | Obtain management approval for project | Consider cost-benefit analysis, staffing, and funding | Project Plan
1.6 | Obtain ITS Project Management Office approval | Enroll with ITS Project Portfolio Management (PPM), if applicable
1.7 | Signup for a Yahoo ID Account | On the Yahoo E-Commerce page, at the link for New User, click "Sign Up" and comlete the enrollment form. Obtain Yahoo ID in an agency's employee name, but use a work address and work email. For alternate email, suggest use employee in fiscal office. Multiple Yahoo IDs may be created, one for each employee being given access to the Yahoo Store ID Account. (Only one Yahoo ID can have access to the Store Account at any one given time.
1.7a | Signup for a Yahoo Store ID | Choose Plan from menu Choose Domain Name Enter Billing Information (For credit card payment option, use agency's Procurement Card) Confirm Order
1.8 | Convenience fees N/A | Conenience fees are not accommodated by Yahoo Stores. Shipping costs are provided for.
Other
2 | Execute Enrollment Forms | Pertains to Merchant Account w/ STMS | Link To Forms | OSC provides all forms on Website | OSC
2.1 | Master Services Agreement (MSA) | Review MSA with STMS. Legal should review agreement. Consider the potential fines and other liabilites.
2.2 | Agency Participation Agreement (APA) | Execute APA. Legal should review agrrement. | APA | OSC approves or disapproves participation. A new APA is not required for subsequently added outlets. | OSC
2.3 | Merchant Card Participant Setup Form | Execute Participate Setup Form - by Chief Fiscal Officer | Merchant Card Participant Setup Form | A new Participant Setup Form is not required for subsequently added outlets.
2.4 | Merchant Card Outlet Setup Form | Execute Outlet Setup Form for the Yahoo Store's merchant number needed - by Fiscal Officer (If agency uses POS terminals, a different merchant number is needed for the agency's Yahoo Store.) | Merchant Card Outlet Setup Form
2.5 | ClientLine Setup Form | Prepare form designating users who will need access to Clientline online reporting with STMS - by Fiscal Officer | ClientLine Setup Form
2.6 | Wachovia Connection Setup Form | Prepare form designating users who will need access to Wachovia Connection online reporting for the Wachovia bank settlement account - by Fiscal Officer | Wachovia Connection Setup Form
3 | OSC Acts on Enrollment Forms
3.1 | Agency Participation Agreement (APA) |  |  | OSC processes agreements with DST and STMS, & distributes | OSC
3.2 | Merchant Card Participant Setup Form |  |  | OSC processes form with DST, STMS, & Wachovia | OSC
|  |  |  | OSC updates the participant info in the Access database, and email contact list | OSC
3.3 | Merchant Card Outlet Setup Form |  |  | OSC processes form with STMS, and updates the Access database with the Merchant info | OSC
3.4 | ClientLine Setup Form |  |  | OSC processes from with STMS, setting up users and obtaining UserIDs and initial passwords. Users are notified directly of their UserIDs and initial passwords. | OSC
3.5 | Wachovia Connection Setup Form |  |  | If OSC is Admin for Wachovia Connection, agency users are set up, and users are notified directly of their UserID and initial password. | OSC
3.6 | PCI Security Validation Services Pre-Enrollment Form |  |  | Agency must be enrolled with Trustwave for the purposes of completing the annual Self Assessment Questionnaire. SAQ-A applies since Yahoo is a service provider. Yahoo must be compliant pursuant to Requirement 12.8. | OSC
4 | DST Acts on Enrollment Forms
4.1 | Agency Participation Agreement (APA) |  |  | DST executes APA | DST
4.2 | Merchant Card Participant Setup Form |  |  | DST authorizes Wachovia to establish settlement account for agency | DST
|  |  |  | DST establishes CIT account on CB$, and maps the ZBA account number when received from Wachovia, if State agency | DST
5 | STMS Acts on Enrollment Forms
5.1 | Agency Participation Agreement (APA) |  |  | STMS executes APA and returns to OSC. Non-State agencies may be subject to a credit check | STMS
5.2 | Merchant Card Participant Setup Form |  |  | STMS sets up profile for agency, assigning a Chain Number tor the agency Merchant Name, and advises OSC | STMS
5.3 | Merchant Card Outlet Setup Form |  |  | STMS assigns a merchant number to each outlet, mapping them to the agency's chain number. Also sets up invoicing. | STMS
5.4 | ClientLine Setup Form |  |  | STMS sets up users and provides UserIDs and initial passwords to OSC, which then notifies each user separately, normally by Fax. | STMS
6 | Establish production environment and Testing
6.1 | Design and build store | Obtain assistance from ITS on design of site
6.2 | Complete menu items | Insert Contact Info, Privacy Policy, etc
6.3 | Establish catalog and pricing | Shopping cart is maintained on Yahoo site. Payment method offered should be merchant cards (allowing FDMS/STMS to be the processor). Do not select PayPal. Setup Shipping and Sales Tax
6.4 | Perform testing of limited transactions | Perform testing within a controlled environment.
6.5 | Resolve Catalog ordering issues | ITS and Yahoo will assist in ordering issues |  | ITS provides assistance is setup of catalog | ITS
6.6 | Resolve agency set-up issues detected with STMS or Wachovia Bank | STMS will assist in transaction issues. OSC will work with Wachovia Bank for any account set-up issues. |  | Make any necessary changes in account mapping on Wachovia Connection. | OSC
|  |  |  | Make any necessary changes in users on ClientLine. | OSC
7 | Establish Business Procedures
7.1 | Educate staff on SECP website | Review presentations, policies, agreements, forms, and contact information
7.2 | Establish procedures for card not-present transactions. | Base procedures on STMS Operating Guide and Card Association Rules. Topics should include, expiration date verification, processing inadvertent duplicate transactions, refunds, chargebacks, etc.
7.3 | Establish procedures for obtaining authorizations | Base procedures on STMS Operating Guide and Card Association Rules. Topics should include, suspected fraud situations (Code 10 Procedures), etc.
7.4 | Provide necessary training for updating the Yahoo Store. | Determine the functions various employees will have regarding maintaining the store. Incorporate instructions provided on Yahoo site, including the various Guides in PDF format found at: http://help.yahoo.com/help/us/store/guides/
7.6 | Establish procedures for retaining transaction records, records retention, and handling disputed transactions. | Devise procedures based on OSC E-Commerc Policies, STMS Operating Guide, and Card Association Rules. Use template on OSC's SECP Website | Internal Policies and Procedures
7.7 | Submit Internal Agency Policies & Procedures | Submit by email to osc.secp.info@osc.nc.gov for review. |  | OSC reviews and approves policies and procedures | OSC
8 | Establish Fiscal Procedures
8.1 | Educate staff on SECP website | Review presentations, policies, agreements, forms, and contact information
8.2 | Establish procedures for reporting of funds received for settlement of transactions; and Refunds and Chargebacks that are netted out of daily ZBA sweep. | Incorporate Reconcilement Function requirements on SECP website. Consider settlement of proprietary card transactions that may be received on a different day than Visa or MasterCard.
8.3 | Establish procedures for Wachovia Connection users | Verify all users have received userIDs and passwords, and have access to all required functions and settlement accounts
8.4 | Establish procedures for ClientLine users | Verify all users have received userIDs and passwords, and have access to all merchant numbers and required reports
8.5 | Establish procedures for multiple merchant numbers settling into same bank account, and associated reconcilement with the decentralized department's captured transactions. | Incorporate Reconcilement Function requirements on SECP website. Settlement of POS transactions may settle into the same bank account as the Yahoo Store settlements.
8.6 | Establlish procedures for reviewing, verifying, and paying STMS monthly invoice | Develop controls, and periodically examine to enusre that the appropriate Interchange rates are being applied.
8.7 | Establlish procedures for reviewing, verifying, and paying Yahoo monthly invoice | Develop controls, and periodically examine to enusre that the appropriate fees are being charged.
8.8 | Prepare an updated Cash Management Plan | Describe Internal Policies and Procedures, incorporating procedures established, and any applicable E-Commerce policies on SECP websie, utilizing sample format. | Internal Policies and Procedures
8.9 | Submit Internal Agency Policies & Procedures | Submit by email to osc.secp.info@osc.nc.gov for review. |  | OSC reviews and approves policies and procedures | OSC
9 | Obtain PCI Security Compliance
9.1 | Educate staff on PCI Security Standards requirements | Review OSC's Website pertaiing to PCI Security, including presentations, policies, Visa and MasterCard Websites. Consider the potential fines for non-compliance or security breaches.
9.2 | Establish procedures from the business perspective | Consider requirement associated with business processing, to include physical security, employee background checks, etc.
9.3 | Establish procedures from the technical perspective | Consider requirement associated with technical processing, to include hardware, software, firewalls, encryption, etc.
9.4 | Complete Self Assessment Questionnaire | Select the appropriate SAQ, likely either SAQ-A.
9.5 | Ascertain compliance of third party providers | Verify that Yahoo Merchant Solutions remains compliant as reflected on Visa's list of compliant service providers
9.6 | Designate individual for PCI Security | Provide one contact for entire agency to OSC, on Merchant Card Participant Setup Form
9.7 | Enroll in TrustKeepr Portal with Trustwave | Since solution involves a completed outsourcing, with only a link to Yahoo, vulnerability scanning is not required, but the annual SAQ is. |  | OSC pre-enrolls the agency in TrustKeeper based on Pre-enrollment form. Agecny must complete the enrollment via TrustKeeper. | OSC
9.8 | Establish Procedures for PCI Remediation | Estabhilsh procedures for compliance deficiencies detected in annual SAQ

## PayPoint
| PayPoint Implementation Plan | Name of Agency: |  |  | Revised |  | 2010-02-18
| Website link for Info | http://www.osc.nc.gov/SECP/SECP_PayPoint.html |  | OSC Support Services Center Contact Info: | 919.707.0795
| PayPoint Support Email Address | PaySupport@firstdata.com |  | PayPoint Help Desk |  | 877-869-0860
NOTE: This plan applies to participants that have enrolled in the PayPoint Gateway Services offered by First Data Government Solultions (FDGS)
| AGENCY ACTIVITIES & TASKS |  |  | OSC & FDGS ACTIVITIES & TASKS
Step | AGENCY ACTIVITIES & TASKS | TASK DESCRIPTION | Agency/Project Deliverables | CORRESPONDING TASKS (OSC Use Only) | By | Target Date | Date Completed
1 | Idenfify PayPoint Web Capture Project |  | Link to PayPoint Info | OSC provides updated Website information and answers any questions asked. | OSC
1.1 | Review information on OSC's SECP Website | Review OSC's presentations, STMS Amendment No. 2, PayPoint Gateway Overview document, and PayPoint Integration Guides/Manuals.
1.2 | Request Demo | View demo of PayPoint features, either from OSC or FDGS |  | Present Power Point Presentation | OSC
1.3 | Idenfity potential payment applications | Determine what agency receipts applications will be utilized for online payments. View other ageny websites using PayPoint (e.g., Dept of Labor)
1.4 | Assess feasibility of implementation | Cost-benfit analysis Includes costs of development, ongoing operation maintaince, and merchant card interchange fees. Consider initial set-up fee of $1,000 paid to FDGS. | Cost-benefit analysis |  | OSC
1.5 | Obtain management approval for project | Consider cost-benefit analysis, staffing, and funding | Project Plan
1.4 | Attend Pre-Project Meeting | Request Pre-Project meetings for discussions. Topics include applications to be utilized; involvement of IT staff. Make determination on various options available | Pre-Project Meeting | OSC conducts meeting and responds to questions (Demo if not already seen) | OSC
1.6 | Determine the Interfacing Option to be utilized: 1) Query String Web Service; or 2) Batch FTP (Applies to each application) | Select the appropriate Interfacing Option. Most agencies select the "Query String Web Service Option," which allows for agency to authenticate an attempted transaction before being passed to PayPoint.
Other
2 | Execute Enrollment Forms | Pertains to Merchant Account w/ STMS | Link To Forms | OSC provides all forms on Website | OSC
2.1 | Master Services Agreement (MSA) | Review MSA with STMS, including Amendment No. 2. Legal should review agreement. Consider the potential fines and other liabilites.
2.2 | Agency Participation Agreement (APA) | Execute APA (Schedule E). If already executed, must re-execute, selecting the PayPoint Gateway Option. | APA - Schedule E | OSC approves or disapproves participation. A new APA is not required for subsequently added applications. | OSC
2.3 | Merchant Card Participant Setup Form | Execute Participate Setup Form, if not currently a paricipant with STMS - by Chief Fiscal Officer | Merchant Card Participant Setup Form | A new Participant Setup Form is not required for subsequently added merchant numbers
2.4 | Merchant Card Outlet Setup Form | Execute Outlet Setup Form for each application to be enrolled on PayPoint. A separate merchant number needed for each application - by Fiscal Officer | Merchant Card Outlet Setup Form
2.5 | ClientLine Setup Form | Prepare form designating users who will need access to ClientLine online reporting with STMS - by Fiscal Officer | ClientLine Setup Form
2.6 | Wachovia Connection Setup Form | Prepare form designating users who will need access to Wachovia Connection online reporting for the Wachovia bank settlement account - by Fiscal Officer | Wachovia Connection Setup Form
2.7 | PCI Security Validation Services Pre-Enrollment Form | Execute PCI Pre-Enrollment Form, if not currently enrolled in TrustKeeper - by Agency's PCI Contact | PCI Data Security Validation Services Pre-Enrollment Form
2.8 | PayPoint Application Boarding Form | As part of the Project Plan conducted by PayPoint, the Boarding Form is to be completed. | PayPoint Boarding Form
3 | OSC Acts on Enrollment Forms
3.1 | Agency Participation Agreement (APA) |  |  | OSC processes agreements with DST and STMS, & distributes | OSC
3.2 | Merchant Card Participant Setup Form |  |  | OSC processes form with DST, STMS, & Wachovia | OSC
|  |  |  | OSC updates the participant info in the Access database, and email contact list | OSC
3.3 | Merchant Card Outlet Setup Form |  |  | OSC processes form with STMS, and updates the Access database with the Merchant info | OSC
3.4 | ClientLine Setup Form |  |  | OSC processes from with STMS, setting up users and obtaining UserIDs and initial passwords. Users are notified directly of their UserIDs and initial passwords. | OSC
3.5 | Wachovia Connection Setup Form |  |  | If OSC is Admin for Wachovia Connection, agency users are set up, and users are notified directly of their UserID and initial password. | OSC
3.6 | PCI Security Validation Services Pre-Enrollment Form (Refer to Section 9 below) |  |  | The agency's chain number is to be enrolled with Trustwave. If PayPoint is to be utilized as a virtual terminal (through Admin screen) the external-facing IP addresses must be enrolled in TrustKeeper for monthly vulnerability scanning | OSC
4 | DST Acts on Enrollment Forms
4.1 | Agency Participation Agreement (APA) |  |  | DST executes APA | DST
4.2 | Merchant Card Participant Setup Form |  |  | DST authorizes Wachovia to establish settlement account for agency, unless one is already set up | DST
|  |  |  | DST establishes CIT account on CB$, and maps the ZBA account number when received from Wachovia, if State agency | DST
5 | STMS and FDGS Act on Enrollment Forms
5.1 | Agency Participation Agreement (APA) |  |  | STMS executes APA and returns to OSC. Non-State agencies may be subject to a credit check | STMS
5.2 | Merchant Card Participant Setup Form |  |  | STMS sets up profile for agency, assigning a Chain Number tor the agency Merchant Name, and advises OSC | STMS
5.3 | Merchant Card Outlet Setup Form |  |  | STMS assigns a merchant number to each outlet, mapping them to the agency's chain number. Also sets up invoicing. | STMS
5.4 | MyMerchant View Setup Form |  |  | STMS sets up users and provides UserIDs and initial passwords to OSC, which then notifies each user separately, normally by Fax. | STMS
5.5 | PayPoint Application Boarding Form |  |  | FDGS sets up application first in the Test Region, and then in the Production Region | FDGS
6 | Establish Training,Testing, and Production | Refer to FDGS Detailed Project Plan
6.1 | Attend Admin Training |  |  | OSC Conducts Training in Test Region | OSC
6.2 | Attend Consumer Interface Training |  |  | OSC Conducts Training in Test Region | OSC
6.3 | Establish Internal Infrastructure and Interfacing
6.4 | Complete Testing in Test Region
6.5 | Complete Testing in Production Region
6.6 | Resolve issued identified in Testing
6.7 | Place into production
7 | Establish Business Procedures |  | Link to Template
7.1 | Educate staff on SECP website | Review presentations, policies, agreements, forms, and contact information
7.2 | Establish procedures for using the Admin Screen feature | Determine how the Admin screen will be used for agency-entered transactions, including issuing refunds and recording chargebacks.
7.3 | Establish procedures for authenticating payers | At least two components of challenge data must be used. Either on agency's site or on PayPoint/
7.4 | Establish procedures for updating PayPoint database and agency's A/R database. | Determine which ones will be automated vs. manual, and frequency
7.5 | Establish procedures for retaining transaction records, records retention, and handling disputed transactions. | Devise procedures based on OSC E-Commerc Policies, STMS Operating Guide, and Card Association Rules. Use template on OSC's SECP Website | Internal Policies and Procedures
7.6 | Establish a help desk function for web payers | Payers that experience problems should be provided both an email address and telephone number. Determined if help provided per agency division or centerally
7.7 | Submit Internal Agency Policies & Procedures | Submit by email to osc.secp.info@osc.nc.gov for review. |  | OSC reviews and approves policies and procedures | OSC
8 | Establish Fiscal Procedures |  | Link to Template
8.1 | Educate staff on SECP website | Review presentations, policies, agreements, forms, and contact information
8.2 | Establish procedures for reporting of funds received for settlement of transactions; and Refunds and Chargebacks that are netted out of daily ZBA sweep. | Incorporate Reconcilement Function requirements on SECP website. Consider settlement of cards vs. E-Checks and how to reconcile with PayPoint reports.
8.3 | Establish procedures for Wachovia Connection users | Verify all users have received userIDs and passwords, and have access to all required functions and settlement accounts
8.4 | Establish procedures for ClientLine users | Verify all users have received userIDs and passwords, and have access to all merchant numbers and required reports
8.5 | Establish procedures for PayPoint users | Verify all users have received userIDs and passwords, and have access to the appropriate roles
8.6 | Establish procedures for multiple merchant numbers settling into same bank account, and associated reconcilement with the decentralized department's captured transactions. | Incorporate Reconcilement Function requirements on SECP website. Settlement of POS transactions may settle into the same bank account as the Yahoo Store settlements.
8.7 | Establlish procedures for reviewing, verifying, and paying STMS and FDGS monthly invoices | Develop controls, and periodically examine to enusre that the appropriate Interchange rates are being applied.
8.8 | Prepare an updated Cash Management Plan | Describe Internal Policies and Procedures, incorporating procedures established, and any applicable E-Commerce policies on SECP websie, utilizing sample format. | Internal Policies and Procedures
8.9 | Submit Internal Agency Policies & Procedures | Submit by email to osc.secp.info@osc.nc.gov for review. |  | OSC reviews and approves policies and procedures | OSC
9 | Validate PCI Compliance |  | Link to PCI Info
9.1 | Educate staff on PCI Security Standards requirements | Review OSC's Website pertaiing to PCI Security, including presentations, policies, Visa and MasterCard Websites. Consider the potential fines for non-compliance or security breaches.
9.2 | Establish procedures from the business perspective | Consider requirement associated with business processing, to include physical security, employee screening, etc.
9.3 | Establish procedures from the technical perspective | Consider requirement associated with technical processing, to include hardware, software, firewalls, encryption, etc.
9.4 | Complete Security Assessment Questionnaire | Select the appropriate SAQ, likely either SAQ-C or SAQ-D. To be completed online annually.
9.5 | Ascertain compliance of third party providers | OSC has already verified that PayPoint is a compliant service provider.
9.6 | Designate individual for PCI Security | Provide one contact for entire agency to OSC, on Merchant Card Participant Setup Form
9.7 | Enroll in TrustKeepr Portal with Trustwave | If the agency will utilze PayPoint as a virtuatl terminal, through the Admin screen, the external-facing IP address must be enrolled for vulnerability scanning. The enrollment should be for both "SAQ and Vulnerability Scanning," with the scanning be perfomed by Trustwave monthly. |  | OSC pre-enrolls the agency in TrustKeeper based on Pre-enrollment form. Agecny must complete the enrollment via TrustKeeper. Agency must specify the external-facing IP addresses to be scanned monthly. | OSC
9.8 | Establish Procedures for PCI Remediation | Estabhilsh procedures for compliance deficiencies detected in annual SAQ or in monthly vulnerability scan